## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | Project planning, coordination and repository setup | Must | None | Srishti | Completed
Sprint 1 | Sprint 1 | US-002 | Create GitHub organization and repository | Must | US-001 | Srishti | Completed
Sprint 1 | Sprint 1 | US-003 | Invite team members as collaborators and configure access | Must | US-002 | Srishti | Completed
Sprint 1 | Sprint 1 | US-004 | Add the MIT License | Should | US-002 | Srishti | Completed
Sprint 1 | Sprint 1 | US-005 | Define project roadmap and milestone plan | Must | US-001 | Srishti | Completed
Sprint 1 | Sprint 1 | US-006 | Upload raw Kaggle employee attrition dataset (15,000 records) | Must | US-005 | Santhosh | Completed
Sprint 1 | Sprint 1 | US-007 | Data loading and structural standardization (column normalization) | Must | US-006 | Santhosh | Completed
Sprint 1 | Sprint 1 | US-008 | Missing value and duplicate record checks | Must | US-007 | Satish | Completed
Sprint 1 | Sprint 1 | US-009 | Categorical and text field cleaning | Should | US-007 | Satish | Completed
Sprint 1 | Sprint 1 | US-010 | Logical consistency validation against business rules | Must | US-008 | Satish | Completed
Sprint 1 | Sprint 1 | US-011 | Binary field encoding and export cleaned dataset | Must | US-009, US-010 | Santhosh | Completed
Sprint 2 | Sprint 2 | US-012 | Create career and tenure engineered features | Must | US-011 | Thivya | Completed
Sprint 2 | Sprint 2 | US-013 | Create salary and income engineered features | Must | US-011 | Thivya | Completed
Sprint 2 | Sprint 2 | US-014 | Create satisfaction and workload engineered features | Must | US-011 | Santhosh | Completed
Sprint 2 | Sprint 2 | US-015 | Create commute, performance and attendance features | Should | US-011 | Srishti | Completed
Sprint 2 | Sprint 2 | US-016 | Categorical encoding and export Featured Engineering dataset | Must | US-012, US-013, US-014, US-015 | Thivya | Completed
Sprint 2 | Sprint 2 | US-017 | Design PostgreSQL star schema (employees / employee_metrics / predictions) | Must | US-016 | Srishti | Completed
Sprint 2 | Sprint 2 | US-018 | Load cleaned and feature-engineered data into PostgreSQL | Must | US-017 | Srishti | Completed
Sprint 2 | Sprint 2 | US-019 | Validate database schema, joins and row counts | Must | US-018 | Srishti | Completed
Sprint 3 | Sprint 3 | US-020 | Perform exploratory data analysis and leakage checks | Must | US-016 | Anil | Completed
Sprint 3 | Sprint 3 | US-021 | Train and evaluate attrition prediction model | Must | US-020 | Surendhar | Completed
Sprint 3 | Sprint 3 | US-022 | Train and evaluate skill-gap prediction model | Must | US-020 | Surendhar | Completed
Sprint 3 | Sprint 3 | US-023 | Generate employee attrition and skill-gap predictions | Must | US-021, US-022 | Surendhar | Completed
Sprint 3 | Sprint 3 | US-024 | Build rule-based AI recommendation engine | Should | US-023 | Gowtham | Completed
Sprint 3 | Sprint 3 | US-025 | Build RAG knowledge base and document chunking | Must | US-005 | Satish | Completed
Sprint 3 | Sprint 3 | US-026 | Implement TF-IDF/FAISS + BM25 hybrid retrieval and RRF | Must | US-025 | Anil | Completed
Sprint 3 | Sprint 3 | US-027 | Implement reranking, context expansion and Groq answer generation | Must | US-026 | Anil | Completed
Sprint 3 | Sprint 3 | US-028 | Test RAG retrieval and grounded answers | Must | US-027 | Satish | Completed
Sprint 4 | Sprint 4 | US-029 | Develop FastAPI backend and PostgreSQL analytics endpoints | Must | US-019, US-024, US-027 | Srishti | Completed
Sprint 4 | Sprint 4 | US-030 | Build web dashboard pages and employee views | Must | US-021, US-022, US-024 | Harshitha | Completed
Sprint 4 | Sprint 4 | US-031 | Implement dashboard charts, risk badges and navigation | Should | US-030 | Gowtham | Completed
Sprint 4 | Sprint 4 | US-032 | Create Power BI Overview page | Should | US-019 | Srishti | Completed
Sprint 4 | Sprint 4 | US-033 | Create Power BI Attrition & Risk page | Should | US-032 | Srishti | Completed
Sprint 4 | Sprint 4 | US-034 | Create Power BI Development & Well-being page | Should | US-032 | Srishti | Completed
Sprint 4 | Sprint 4 | US-035 | Run backend endpoint and frontend page testing | Must | US-029, US-030 | Surendhar | Completed
Sprint 4 | Sprint 4 | US-036 | Fix route and integration issues and re-test | Must | US-035 | Surendhar | Completed
Sprint 4 | Sprint 4 | US-037 | Deploy frontend/backend finalize environment configuration | Must | US-029, US-030, US-036 | Thivya | Completed
Sprint 4 | Sprint 4 | US-038 | Finalize project documentation and repository | Should | US-037 | Srishti | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 163 | 69 | 77 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T-001 | Project planning, coordination and repository setup | 31-Jul-26 | 31-Jul-26 | Srishti | Plan | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-002 | Create GitHub organization and repository | 31-Jul-26 | 31-Jul-26 | Srishti | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-003 | Invite team members and configure repository access | 31-Jul-26 | 01-Aug-26 | Srishti | Plan | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-004 | Add MIT License and repository files | 01-Aug-26 | 02-Aug-26 | Srishti | Build | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T-005 | Define roadmap and implementation strategy | 01-Aug-26 | 03-Aug-26 | Harshitha | Plan | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T-006 | Upload raw Kaggle employee attrition dataset | 01-Aug-26 | 01-Aug-26 | Santhosh | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T-007 | Normalize columns and audit data types | 01-Aug-26 | 02-Aug-26 | Santhosh | Code | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T-008 | Check missing values and duplicates | 02-Aug-26 | 02-Aug-26 | Satish | Test | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T-009 | Clean categorical and text fields | 02-Aug-26 | 03-Aug-26 | Satish | Code | 3- Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T-010 | Validate business rules and logical consistency | 03-Aug-26 | 04-Aug-26 | Satish | Test | 3- Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | T-011 | Encode binary fields and export cleaned dataset | 04-Aug-26 | 05-Aug-26 | Santhosh | Build | 3- Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-012 | T-012 | Create career and tenure engineered features | 10-Aug-26 | 12-Aug-26 | Thivya | Code | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | T-013 | Create salary and income engineered features | 11-Aug-26 | 13-Aug-26 | Thivya | Code | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | T-014 | Create satisfaction and workload features | 12-Aug-26 | 14-Aug-26 | Santhosh | Code | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | T-015 | Create commute, performance and attendance features | 13-Aug-26 | 15-Aug-26 | Srishti | Code | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | T-016 | Encode categories and export 63-column dataset | 15-Aug-26 | 18-Aug-26 | Thivya | Build | 3- Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | T-017 | Design PostgreSQL schema | 16-Aug-26 | 18-Aug-26 | Srishti | Design | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-018 | T-018 | Load data into PostgreSQL with ETL | 18-Aug-26 | 21-Aug-26 | Srishti | Build | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-019 | T-019 | Validate joins and row counts | 21-Aug-26 | 22-Aug-26 | Srishti | Test | 3- Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-020 | T-020 | EDA and leakage analysis | 20-Aug-26 | 22-Aug-26 | Anil | Test | 3- Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-021 | T-021 | Train attrition Random Forest model | 23-Aug-26 | 26-Aug-26 | Surendhar | Code | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-022 | T-022 | Train skill-gap LightGBM model | 25-Aug-26 | 28-Aug-26 | Surendhar | Code | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-023 | T-023 | Generate model prediction outputs | 28-Aug-26 | 30-Aug-26 | Surendhar | Build | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-024 | T-024 | Build rule-based recommendation engine | 29-Aug-26 | 01-Sep-26 | Gowtham | Code | 3- Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-025 | T-025 | Create RAG knowledge base and chunk documents | 28-Aug-26 | 30-Aug-26 | Satish | Code | 3- Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-026 | T-026 | Implement TF-IDF/FAISS + BM25 hybrid retrieval | 30-Aug-26 | 02-Sep-26 | Anil | Code | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-027 | T-027 | Implement RRF, reranking and context expansion | 01-Sep-26 | 03-Sep-26 | Anil | Code | 3- Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-028 | T-028 | Test RAG retrieval and grounded responses | 03-Sep-26 | 05-Sep-26 | Satish | Test | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-029 | T-029 | Develop FastAPI backend and analytics endpoints | 01-Sep-26 | 05-Sep-26 | Srishti | Code | 3- Completed | 7 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-030 | T-030 | Build web dashboard pages and employee views | 02-Sep-26 | 06-Sep-26 | Harshitha | Build | 3- Completed | 7 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-031 | T-031 | Implement dashboard charts, risk badges and navigation | 04-Sep-26 | 07-Sep-26 | Gowtham | Design | 3- Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-032 | T-032 | Create Power BI Overview page | 05-Sep-26 | 07-Sep-26 | Srishti | Design | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-033 | T-033 | Create Power BI Attrition & Risk page | 06-Sep-26 | 08-Sep-26 | Srishti | Design | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-034 | T-034 | Create Power BI Development & Well-being page | 07-Sep-26 | 09-Sep-26 | Srishti | Design | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-035 | T-035 | Run backend and frontend testing suites | 08-Sep-26 | 10-Sep-26 | Surendhar | Test | 3- Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-036 | T-036 | Fix route/integration issues and re-test | 10-Sep-26 | 11-Sep-26 | Surendhar | Test | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-037 | T-037 | Deploy frontend/backend and configure environment | 11-Sep-26 | 13-Sep-26 | Thivya | Build | 3- Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-038 | T-038 | Finalize documentation and repository | 13-Sep-26 | 15-Sep-26 | Srishti | Documentation | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken | Internship Period
1 | Day 14 (13-Aug-26) | Supabase authentication and environment variables failed during ETL. | Reset credentials and loaded .env using explicit project path. | 31-Jul-26 to 15-Sep-26 (47 calendar days)
2 | Day 15 (14-Aug-26) | Schema execution timed out and large insert showed no progress. | Applied schema once in SQL Editor and changed to 500-row batched inserts. | Day 1 = 31-Jul-26; Day 47 = 15-Sep-26
2 | Day 21 (20-Aug-26) | Boolean fields caused a PostgreSQL datatype mismatch. | Cast five flag columns from 0/1 integers to Python bool before insert.
3 | Day 29 | Attrition_Risk_Score raised a possible leakage concern. | Excluded the raw risk-score column before model training.
3 | Day 30 | Skill-gap target lacked a ground-truth HR assessment label. | Created and documented a synthetic proxy label with weighted rules plus noise.
3 | Day 33 | RAG deployment footprint was too large for the target free tier. | Replaced neural embeddings with TF-IDF/FAISS and BM25 hybrid retrieval.
3 | Day 34 | Some RAG queries returned less relevant chunks. | Tuned RRF and added TF-IDF reranking plus context expansion.
3 | Day 41 | Frontend page smoke test exposed a missing employee_id route parameter. | Fixed the route handler and re-ran the complete page-testing suite.
4 | Day 43 | Deployment required separate frontend/backend configuration. | Configured DB_* and GROQ_API_KEY variables and separated services.
4 | Day 47 | Final documentation needed alignment with implemented features. | Updated report, testing evidence, Agile and defect documentation.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-31 | 2026-08-13 | Srishti | Track environment setup and ETL progress daily. | Waiting for infrastructure issues to surface before escalation. | Keep repository and task ownership clear. | Added explicit environment checks and clearer task ownership.
2 | Sprint 2 | 2026-08-14 | 2026-08-27 | Santosh | Add validation checks before feature engineering. | Passing inconsistent raw assumptions downstream. | Document feature definitions and dependencies. | Added validation and documented engineered features.
3 | Sprint 3 | 2026-08-28 | 2026-09-10 | Anil | Test retrieval quality with representative policy questions. | Using a single retrieval method without relevance checks. | Keep model/RAG tests reproducible. | Added hybrid retrieval, reranking and RAG test query.
4 | Sprint 4 | 2026-09-11 | 2026-09-15 | Surendhar | Run regression tests after every route/integration fix. | Closing issues without a full re-test. | Keep testing evidence linked to final deliverables. | Re-ran frontend/backend suites after fixes and finalized QA documentation.
5 | Sprint 4 | 2026-09-15 | 2026-09-15 | Srishti | Complete final documentation, Agile records and defect tracker. | Leaving final documentation until after the internship period. | Keep documentation synchronized with the implemented project. | Finalized documentation, Agile records and QA/defect evidence .