## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Srishti | 2026-07-31 | Repository initially lacked required documentation, license and community health files. | Sprint 1 | Srishti | Maintainability | Added MIT License, README and required repository files. | 2026-07-31 | Closed | Repository setup completed.
2 | Srishti | 2026-08-01 | Project implementation approach required clarification between a Power BI-only dashboard and a combined ML + RAG-based solution. | Sprint 1 | Srishti | Requirement | Discussed the approach with the team and mentor and finalized the end-to-end roadmap. | 2026-08-01 | Closed | Team aligned on the implementation strategy.
3 | Santosh | 2026-08-02 | Raw dataset column headers were in mixed/Title case and inconsistent, complicating downstream cleaning. | Sprint 1 | Santosh | Standards | Normalized all column names to lowercase and stripped whitespace. | 2026-08-02 | Closed | Dataset ready for structural validation.
4 | Satish | 2026-08-03 | Numeric fields contained outliers that could distort feature distributions if not reviewed. | Sprint 1 | Satish | Logical | Applied IQR-based outlier detection and reviewed high-income outliers individually rather than removing them. | 2026-08-04 | Closed | Outliers retained as legitimate data after review.
5 | Srishti | 2026-08-04 | Database connection failed with 'password authentication failed (28P01)' when loading data into Supabase. | Sprint 1 | Srishti | Environment | Reset the database password in Supabase and stored the raw, unencoded value in DB_PASSWORD. | 2026-08-05 | Closed | Connection established successfully.
6 | Srishti | 2026-08-05 | .env file variables were not being picked up at runtime, causing missing database credentials. | Sprint 1 | Srishti | Environment | Loaded the .env file via an explicit absolute path instead of relying on the working directory. | 2026-08-06 | Closed | Environment variables loaded correctly.
7 | Srishti | 2026-08-06 | Schema DDL execution through the pooled Supabase connection triggered a QueryCanceled: statement timeout error. | Sprint 1 | Srishti | Environment | Applied schema.sql once directly in the Supabase SQL Editor and added a table-existence check to skip DDL on later runs. | 2026-08-07 | Closed | Schema applied without further timeouts.
8 | Srishti | 2026-08-07 | Bulk insert of 15,000 rows appeared to hang with no progress feedback during ETL loading. | Sprint 1 | Srishti | Logical | Switched to batched inserts (execute_values, page_size=500) with progress print statements. | 2026-08-08 | Closed | Load completed with visible progress and no hangs.
9 | Srishti | 2026-08-08 | DatatypeMismatch error occurred because flag columns were stored as 0/1 integers while the schema defined them as BOOLEAN. | Sprint 1 | Srishti | Logical | Explicitly cast the five flag columns to Python bool before insertion. | 2026-08-09 | Closed | Data loaded into PostgreSQL without type errors.
10 | Anil | 2026-08-20 | The dataset's built-in Attrition_Risk_Score was found to correlate very strongly with the Attrition target, risking data leakage. | Sprint 2 | Harshitha | Logical | Flagged the column as a leakage risk during EDA and excluded it from the Featured Engineering dataset and model training. | 2026-08-21 | Closed | Leakage risk removed before modeling.
11 | Surendhar | 2026-08-22 | No ground-truth HR skills-assessment label existed to train the skill-gap prediction model. | Sprint 2 | Surendhar | Requirement | Built a synthetic proxy label from a weighted rule plus noise and documented it as a proxy-risk predictor rather than a validated assessment. | 2026-08-23 | Closed | Model documented accurately as a proxy predictor.
12 | Satish | 2026-08-29 | The planned RAG embedding stack (sentence-transformer models) risked exceeding Render's free-tier deployment size limit. | Sprint 3 | Satish | Deployment | Rebuilt the retrieval stack around lightweight TF-IDF vectorization and FAISS instead of a neural embedding model. | 2026-08-30 | Closed | RAG platform deploys within Render's free-tier limits.
13 | Anil | 2026-09-02 | Initial hybrid retrieval testing surfaced irrelevant chunks for some workforce-policy questions. | Sprint 3 | Anil | Functional | Tuned Reciprocal Rank Fusion parameters and added TF-IDF cosine reranking with context expansion. | 2026-09-03 | Closed | Retrieval relevance improved and validated.
14 | Satish | 2026-09-04 | Chat endpoint returned a generic error when GROQ_API_KEY was missing during initial backend testing. | Sprint 3 | Satish | Environment | Documented the required GROQ_API_KEY environment variable and verified the configuration-error message behaves as intended. | 2026-09-05 | Closed | Chat endpoint validated with and without the key configured.
15 | Surendhar | 2026-09-10 | Frontend page smoke tests failed for the Employee Details page due to a missing employee_id route parameter. | Sprint 4 | Surendhar | Functional | Fixed the route handler and re-ran the full frontend page-testing suite. | 2026-09-10 | Closed | All frontend pages passed testing.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others